| Workgroup Name: CHIP Nutritious Food Access Workgroup |  |
| --- | --- |
| Charter Version/Date: 1.0/June 19, 2025 |  |
| Subject: Our CHIP goal - Increasing Access to and Consumption of Nutritious Foods Year-Round |  |
| Problem/Opportunity Statement: We are committed to ensuring that all Sierra County residents have access to nutritious foods year-round. By supporting local food systems and improving food security, we aim to provide sustainable, nutritious food options that are fresh when seasonably possible. Through clear communication, coordination of resources, and skill-building, we empower our community to continue the tradition of self-reliance, strengthening our bonds and ensuring we all thrive together. |  |
| Chairperson/Workgroup Lead: Carol Torimino and Melanie Del Carlo |  |
| Team Members, Areas of Expertise, and Roles |  |
| Name, Organization/Affiliation | Areas of Expertise to This Workgroup and Roles |
| Sean Snider | Sierra Plumas Joint Unified School District - Superintendent |
| Randy Jones | Sierra Plumas Joint Unified School District – Office of Ed. |
| Carol Torimino | Eastern Plumas Health Care – Care Management |
| Barbara Daughtrey | Behavioral Health – Peer Mentor |
| Jamie Shiltz | Sierra County Social Services – Social Work Supervisor |
| Sydni Aguirre | Partnership Healthplan – Sierra County Liaison |
| Melanie Del Carlo | Sierra County Public Health Department – PH Educator |
| Tina Slowan-Pomeroy | Sierra County Public Health Department - Epidemiologist |
| Action Plan |  |
| Scope: - This work group will brainstorm strategies, develop SMARTIE objectives and indicators, create an implementation and evaluation plan, and help oversee progress. - Identify other community members and/or organizations to be involved, contact them to gauge their interest, and invite them to future CHIP meetings. - After final workplan, evaluation, and tracking details are finalized, the workgroup will present at a community-wide event, gather feedback, and celebrate progress. The workgroup will not be solely responsible for the ongoing workplan; the CHIP advisory committee will also be involved for additional support, coordination, and communication. |  |
| Considerations: - The amount of time and resources each workgroup member has available to volunteer for this workgroup, which may affect their participation. - Others TBD. |  |

| Available Resources: - Workgroup member time to attend meetings and complete tasks according to the action plan - Meeting spaces and places – Loyalton Social Hall, SNCS Loyalton Office, others TBD - Funds set aside for food to be provided at meetings and events |  |  |
| --- | --- | --- |
| Key Stakeholders: - Advisory committee: We can update them about our progress during meetings and establish a process to let them know when new community members and/or organizations are added. Existing partner organizations: High Sierras Family Resource Center (FRC), First5 Sierra, Partnership Healthplan, Eastern Plumas Health Care (EPHC), Sierra Nevada Children’s Services (SNCS), Mom’s Meals. |  |  |
| Goals and Objectives |  |  |
| Goals | Objectives | Process Metrics |
| Increasing Access to and Consumption of Nutritious Foods Year-Round |  |  |
| Communications Plan |  |  |
| Regular meeting time and location: | - 2nd Wednesday every other month (online calendar invite) from 12-1PM - Loyalton Social Hall (105 Beckwith St. Loyalton, CA. 96118) |  |
| Preferred method of communication: | - Email to entire workgroup |  |
| Tracking Progress |  |  |
| Reporting: | - Discuss items to report each month during the workgroup meeting. - Workgroup lead (TBD) emails the core group and advisory committee and announces updates at meetings. |  |
| Accountability Mechanisms: |  |  |
| - Meeting Minutes (posted on the Sierra County CHIP website) |  |  |